## Sheet1
SAP Solution Documentation Evaluation
Copyright & License Properietary and Conidential. This document can be used royalty free by your organization for commercial or non-comercial purposes. No part of the document can be re-sold, repurposed and made available for sale, download on a public or private website.

## Project Plan
Tasks | RACI |  | Perquisites | 3 weeks duration
| Responsible | Consulted |  | Day-1 | Day-2 | Day-3 | Day-4 | Day-5 | Day-6 | Day-7 | Day-8 | Day-9 | Day-10 | Day-11 | Day-12 | Day-13 | Day-14 | Day-15 | Day-16 | Day-17 | Day-18 | Day-19 | Day-20 | Day-21
Technical Installation and Configuration | bar: 3 weeks duration Day-1 to 3 weeks duration Day-5; 3 weeks duration Day-8 to 3 weeks duration Day-12; 3 weeks duration Day-15 to 3 weeks duration Day-19
Solman System Build (Rec: Two system landscape is recommended for Solution Manager projects) |  |  | X
Run System Preparation |  |  | X
Basic Configuration |  |  | X
Infrastructure Preparation |  |  | X
Enable Process Management Workcenter |  |  | X
Import SAP best practice content into solution manager |  |  | X
Managed system setup of systems in proposed solution |  |  | X
Configure Embedded Search in Solman Dev, Prod |  |  | X
OSS Support Configuration |  |  | X
Workshops and Discovery | bar: 3 weeks duration Day-1 to 3 weeks duration Day-5; 3 weeks duration Day-8 to 3 weeks duration Day-12; 3 weeks duration Day-15 to 3 weeks duration Day-19
Stakeholder Workshops, Discovery, Demo solution documentation. | bar: 3 weeks duration Day-1
Document Folder Structure Layout (Recomendation: Create folders structure which represent the organization business units) | bar: 3 weeks duration Day-2
Present change management options for solution documentation. Decision: Yes/No | bar: 3 weeks duration Day-3
Capture requirements for custom views in solution documentation. Decision Yes/No | bar: 3 weeks duration Day-3
BPML Tool, Decision Yes/No | bar: 3 weeks duration Day-3
Develop organizational process and governance structure for business process documentation | bar: 3 weeks duration Day-4 to 3 weeks duration Day-5
Develop documentation standards for all artifacts to be used during the project life cycle. | bar: 3 weeks duration Day-4 to 3 weeks duration Day-5
Solution Documentation | bar: 3 weeks duration Day-1 to 3 weeks duration Day-5; 3 weeks duration Day-8 to 3 weeks duration Day-12; 3 weeks duration Day-15 to 3 weeks duration Day-19
Configure solution documentation module ( in both Dev and prod systems ) | bar: 3 weeks duration Day-1 to 3 weeks duration Day-5
Create Solution for the SAP landscape. (Recomendation: One Solution is enough of most scenarios) | bar: 3 weeks duration Day-4 to 3 weeks duration Day-5; 3 weeks duration Day-8
Configure Branches | bar: 3 weeks duration Day-4 to 3 weeks duration Day-5; 3 weeks duration Day-8
Create business process folder structure for use in solution documentation | bar: 3 weeks duration Day-8 to 3 weeks duration Day-9
Enable change management | bar: 3 weeks duration Day-9 to 3 weeks duration Day-10
Training | bar: 3 weeks duration Day-1 to 3 weeks duration Day-5; 3 weeks duration Day-8 to 3 weeks duration Day-12; 3 weeks duration Day-15 to 3 weeks duration Day-19
Setup training environment in Solman Dev | bar: 3 weeks duration Day-8 to 3 weeks duration Day-9
Create Training / End User Guide | bar: 3 weeks duration Day-8 to 3 weeks duration Day-10
Train project teams to on - Solution documentation functions - Process steps documentation - Change management for soldoc if enabled | bar: 3 weeks duration Day-11 to 3 weeks duration Day-12
Security | bar: 3 weeks duration Day-1 to 3 weeks duration Day-5; 3 weeks duration Day-8 to 3 weeks duration Day-12; 3 weeks duration Day-15 to 3 weeks duration Day-19
Develop custom roles using SAP Template roles | bar: 3 weeks duration Day-4 to 3 weeks duration Day-5; 3 weeks duration Day-8 to 3 weeks duration Day-10
Provision user access | bar: 3 weeks duration Day-9 to 3 weeks duration Day-10
Security Support | bar: 3 weeks duration Day-11 to 3 weeks duration Day-12; 3 weeks duration Day-15 to 3 weeks duration Day-19
Solution Documentation | bar: 3 weeks duration Day-1 to 3 weeks duration Day-5; 3 weeks duration Day-8 to 3 weeks duration Day-12; 3 weeks duration Day-15 to 3 weeks duration Day-19
Configuration Validation demo to stake holders | bar: 3 weeks duration Day-12; 3 weeks duration Day-15
Prepare test script | bar: 3 weeks duration Day-12; 3 weeks duration Day-15
Testing and Sign off | bar: 3 weeks duration Day-16 to 3 weeks duration Day-18
Go-Live |  |  |  | 3 weeks duration Day-19: Go-live
Production support
Upload existing Organization / SAP project documents into Solution Manager
Document business process hierarchy using SAP BPML tool